## Summary Dashboard
AGILE SPRINT PLAN — NGO Events Platform MVP
4 Weeks ¦ 4 Sprints ¦ 2-Person Team ¦ April 2026
Sprint | Theme | Key Deliverables | Success Criteria | Est Hours | Actual Hours
Sprint 1 (Week 1) | Foundation & Infrastructure | Auth, RBAC, Room CRUD, Admin Dashboard shell | User can register, login, create rooms | 47 | 39
Sprint 2 (Week 2) | Live Video & Attendance | LiveKit video, form builder, attendance collection | Organizer can record and collect attendance | 47 | 39
Sprint 3 (Week 3) | Offline & Reports | PWA offline sync, PDF/Excel reports, Super Admin | Works offline, generates reports | 43 | 0
Sprint 4 (Week 4) | Ship It | i18n, deployment, security, bug fixes, polish | MVP live in production | 44 | 4
|  |  | TOTAL | 181 | 82
Priority Legend
P0 | Must ship — MVP fails without this
P1 | Should ship — can defer if needed
P2 | Nice to have — only with spare capacity
Deferred to Post-MVP
Government / Funder Portal (Phase 2)
YouTube Live fallback streaming (Phase 2)
Monthly / Yearly aggregated reports (Phase 2)
Duplicate attendee detection (Phase 2)
Microsoft SSO (Phase 2)
Advanced analytics dashboard (Phase 2)
Notification system (Phase 2)
Additional languages beyond Hindi/English (Phase 3)

## Sprint 1 - Foundation
Ticket ID | Task / User Story | Owner | Priority | Status | Est (hrs) | Actual (hrs) | Notes / Blockers
PROJECT SETUP & INFRASTRUCTURE
S1-001 | Initialize monorepo (React + Node.js + shared config) | Dev | P0 | Completed | 3 | 3 | Structure ready
S1-002 | Docker Compose setup (API, DB, Redis) | Dev | P0 | Completed | 3 | 3
S1-003 | PostgreSQL schema v1 (users, orgs, roles, events) | Dev | P0 | Completed | 4 | 4 | Schema must be solid - migrations later are costly
S1-004 | CI/CD pipeline (GitHub Actions: lint, test, build) | Dev | P1 | Completed | 2 | 2
S1-005 | Environment config (.env, secrets management) | Dev | P0 | Completed | 1 | 1
AUTHENTICATION & AUTHORIZATION
S1-006 | JWT auth (register, login, refresh token rotation) | Dev | P0 | Completed | 4 | 4
S1-007 | Google OAuth 2.0 SSO integration | Dev | P1 | Completed | 3 | 3
S1-008 | RBAC middleware (Super Admin, NGO Admin, Organizer) | Dev | P0 | Completed | 3 | 3
S1-009 | Login / Register UI pages (responsive) | Dev | P0 | Completed | 3 | 3 | Mobile-first design
ROOM MANAGEMENT (BASIC)
S1-010 | Room CRUD API (create, read, update, delete) | Dev | P0 | Completed | 3 | 3
S1-011 | Room status lifecycle (Scheduled / Live / Ended) | Dev | P0 | Completed | 2 | 2
S1-012 | Unique shareable room link generation | Dev | P0 | Completed | 1 | 1
S1-013 | Create Event Room UI (form + validation) | Dev | P0 | Completed | 3 | 3
S1-014 | NGO Admin Dashboard shell (sidebar, layout, event list) | Dev | P0 | Completed | 4 | 4
PM TASKS
S1-P01 | Set up project board (GitHub Projects / Trello) | PM | P0 | Completed | 2
S1-P02 | Create test cases for auth flows | PM | P0 | Completed | 2
S1-P03 | Test all completed features, file bugs | PM | P0 | Completed | 3 |  | File bugs immediately, do not batch
S1-P04 | Prepare Sprint 1 demo | PM | P0 | Completed | 1
SPRINT 1 TOTALS |  |  |  |  | 47 | 39

## Sprint 2 - Core Features
Ticket ID | Task / User Story | Owner | Priority | Status | Est (hrs) | Actual (hrs) | Notes / Blockers
LIVE VIDEO / STREAMING
S2-001 | LiveKit server setup (self-hosted on Hostinger) | Dev | P0 | Completed | 4 | 4 | HIGHEST RISK TASK - escalate early if blocked
S2-002 | WebRTC integration: start/stop/pause recording controls | Dev | P0 | Completed | 5 | 5
S2-003 | Live stream viewer (NGO Admin can watch active rooms) | Dev | P0 | Completed | 3 | 3 | Defer if S2-001 overruns
S2-004 | Auto-save recording to Cloudflare R2 on session end | Dev | P0 | Completed | 3 | 3
S2-005 | Room status auto-transition (Scheduled to Live to Ended) | Dev | P0 | Completed | 2 | 2
DYNAMIC ATTENDANCE FORM
S2-006 | Form Builder API (CRUD for dynamic field definitions) | Dev | P0 | Completed | 4 | 4
S2-007 | Form Builder UI (drag-and-drop field add/remove/reorder) | Dev | P0 | Completed | 5 | 5
S2-008 | Supported field types: text, number, dropdown, date, checkbox, photo | Dev | P0 | Completed | 3 | 3
S2-009 | Attendance submission API (save entries per event) | Dev | P0 | Completed | 2 | 2
ATTENDANCE COLLECTION UI
S2-010 | Mobile-responsive attendance form (Organizer view) | Dev | P0 | Completed | 4 | 4 | Test on 320px width
S2-011 | Photo capture integration (device camera) | Dev | P0 | Completed | 2 | 2 | Compress to 500KB max
S2-012 | Live attendee count (real-time via Redis pub/sub) | Dev | P1 | Completed | 2 | 2
PM TASKS
S2-P01 | Test video recording on 3G/slow connections | PM | P0 | To Do | 2
S2-P02 | Test form builder with 10+ field configurations | PM | P0 | To Do | 2
S2-P03 | Test attendance form on mobile devices (Android + iOS) | PM | P0 | To Do | 3
S2-P04 | Prepare Sprint 2 demo | PM | P0 | To Do | 1
SPRINT 2 TOTALS |  |  |  |  | 47 | 39

## Sprint 3 - Offline & Reports
Ticket ID | Task / User Story | Owner | Priority | Status | Est (hrs) | Actual (hrs) | Notes / Blockers
OFFLINE / PWA
S3-001 | PWA setup (service worker, manifest, installable) | Dev | P0 | To Do | 3
S3-002 | IndexedDB queue for offline attendance submissions | Dev | P0 | To Do | 4
S3-003 | Auto-sync on reconnection + conflict handling | Dev | P0 | To Do | 3
S3-004 | Offline indicator UI + sync status feedback | Dev | P1 | To Do | 2
REPORTING ENGINE
S3-005 | Report template builder API (JSON config storage) | Dev | P0 | To Do | 3
S3-006 | Report template builder UI (select fields/sections) | Dev | P0 | To Do | 3
S3-007 | Per-event PDF report generation (Puppeteer) | Dev | P0 | To Do | 4
S3-008 | Per-event Excel report generation (ExcelJS) | Dev | P0 | To Do | 3
S3-009 | Report download API (time-limited signed URLs) | Dev | P0 | To Do | 2
SUPER ADMIN & ORG MANAGEMENT
S3-010 | Super Admin panel: create/manage NGO orgs | Dev | P0 | To Do | 3
S3-011 | NGO Admin: invite/manage Event Organizer accounts | Dev | P0 | To Do | 3
S3-012 | Email invitation flow (invite link + password setup) | Dev | P1 | To Do | 2
PM TASKS
S3-P01 | Test offline: airplane mode, fill forms, reconnect, verify sync | PM | P0 | To Do | 3
S3-P02 | Test report generation with real event data | PM | P0 | To Do | 2
S3-P03 | Validate report PDF layout and data accuracy | PM | P0 | To Do | 2
S3-P04 | Prepare Sprint 3 demo | PM | P0 | To Do | 1
SPRINT 3 TOTALS |  |  |  |  | 43 | 0

## Sprint 4 - Ship It
Ticket ID | Task / User Story | Owner | Priority | Status | Est (hrs) | Actual (hrs) | Notes / Blockers
INTERNATIONALIZATION
S4-001 | i18n setup (react-i18next, externalized strings) | Dev | P0 | To Do | 3
S4-002 | Hindi translation for all UI strings | Dev | P0 | To Do | 3 |  | PM to provide/review translations
S4-003 | Language toggle (instant switch, no reload) | Dev | P0 | To Do | 1
DEPLOYMENT & INFRASTRUCTURE
S4-004 | DigitalOcean droplet setup (Docker, Nginx, SSL) | Dev | P0 | To Do | 4
S4-005 | Cloudflare R2 bucket configuration (production) | Dev | P0 | To Do | 2
S4-006 | PostgreSQL production setup + automated backups | Dev | P0 | To Do | 2
S4-007 | CI/CD deploy to staging + production (GitHub Actions) | Dev | P0 | To Do | 3
S4-008 | Domain, DNS, SSL certificate setup | Dev | P0 | To Do | 1
SECURITY & HARDENING
S4-009 | API rate limiting (100 req/min per user) | Dev | P0 | Completed | 2 | 2
S4-010 | Input validation/sanitization on all endpoints | Dev | P0 | Completed | 2 | 2
S4-011 | AES-256 encryption at rest for attendee data | Dev | P1 | To Do | 2
BUG FIXES & POLISH
S4-012 | Bug fix buffer (reserved for Sprint 1-3 bugs) | Dev | P0 | To Do | 6 |  | Track bug count from prior sprints
S4-013 | UI polish: loading states, error messages, empty states | Dev | P1 | To Do | 3
PM TASKS
S4-P01 | Full end-to-end user journey test (all roles) | PM | P0 | To Do | 4
S4-P02 | Hindi language QA (all screens) | PM | P0 | To Do | 2
S4-P03 | Production smoke test post-deployment | PM | P0 | To Do | 2
S4-P04 | Prepare final stakeholder demo | PM | P0 | To Do | 2
SPRINT 4 TOTALS |  |  |  |  | 44 | 4

## Sheet1
New intergation
Per event activity list and there respective clicked images on tape
Create Project
new
It will be same as like a CREATE EVENT (EVENTLY) project, but in this we have to add projects that will be of 2 year or more than a year.